## Sheet1
ProjectName | AspectItemName | Auditees | ConductedBy | DateRecorded | ObservationalComment | Satisfactory | WeatherObservations
TMR - Warrego Hwy (Toowoomba to Dalby) | Visible dust emissions controlled | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | All loads entering or leaving the site are covered and are not generating nuisance dust | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Hours of operation are complied with | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Property condition / dilapidation surveys have been conducted as required | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM | Works are in close proximity to residential receivers | No | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Appropriate drainage and ESC controls have been installed prior to work areas being cleared or disturbed | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Clean' water is being appropriately diverted around/through the site | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of scouring or other erosion within the project areas | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | All stockpiles are protected with appropriate drainage and erosion controls | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Sediment traps are free from damage and of excessive sediment deposition | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Sediment-laden stormwater is not flowing around the sediment fences or other sediment traps | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | All reasonable and practicable measures are being taken to control sediment runoff from the site | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Non-active work areas and other stabilised surfaces have a minimum 70% soil coverage | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | The site is adequately prepared for imminent and forecasted storms | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | All ESC measures are in proper working order | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | The water within sediment basins/excavations has been appropriately tested, and treated as required, to meet the required water quality prior to discharge as per the EMP | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of ponded or stagnant water | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | When working with in a waterway, all regulatory codes are in place and adhered to | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Topsoil and subsoil stockpiles are clearly signed and delineated from each other | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | All stockpiles located away from trees and drip lines | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Cultural Heritage requirements implemented as per Client direction and/or ENV P02 | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Any unexpected CH finds have been managed in accordance with the CEMP and/or ENV P02, including stopping of works in the area | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Storage of fuel/chemicals in accordance with AS1940, bunded appropriately and at distances per EMP away from drainage lines or a water course | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Safety Data Sheets (SDS) readily available for all chemicals | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | All chemicals clearly labelled | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Refuelling areas are bunded and spill kits are available | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Spill trays are being used when refuelling and not being conducted near waterways or drainage lines | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Bunds at full capacity free from rain water or spill | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Evidence of spills/ cleanup? All spills have been reported as an Environmental Incident | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Spill kits are fully stocked, including instructions/procedures for use. | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Spill kits are fully stocked, including instructions/procedures for use. | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Spill kit locations are sign-posted | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Waste oil stored/ disposed of appropriately - No leaks, spills, stains. | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Batteries stored and disposed of appropriately | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Contaminated soil/ waste segregated | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Waste is segregated appropriately for recycling | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Site free of litter/general waste/ cigarette butts | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Traffic control devices / signage correctly installed | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Regulated waste is disposed of and stored correctly | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Concrete waste is stored in a signed, lined and bunded pit | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | ENV05 Waste Materials Tracking Register up to date, and service provider dockets for Waste disposal available | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of native fauna within the projects area (No deaths, injuries or encounters) | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Significant/restricted vegetation flagged and protected | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Existing “Retained” flora is healthy and undisturbed | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Site vehicles using designated site access roads/tracks only | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of pest animals within the projects area | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of declared weeds within the projects area, access roads or right of ways | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Are vehicle weed hygiene inspection reports current and on file? | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Are stockpiled materials free from weed/pest infestation? | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | No exposed areas requiring rehabilitation | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | No mulching required (use mulch from clearing activities) | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | All soil surfaces are being appropriately prepared (i.e. pH, nutrients, roughness and density) prior to revegetation | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Rehabilitation specifics carried out as per EMP | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Stockpiles removed or stabilised and seeded as per EMP | DarrenTest | DarrenTest | 1/25/2014 12:03:00 AM |  | Yes | overcast, light rain
TMR - Warrego Hwy (Toowoomba to Dalby) | Visible dust emissions controlled | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM | high wind gusts are generating visible dust | No | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | All loads entering or leaving the site are covered and are not generating nuisance dust | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Hours of operation are complied with | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Property condition / dilapidation surveys have been conducted as required | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Appropriate drainage and ESC controls have been installed prior to work areas being cleared or disturbed | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Clean' water is being appropriately diverted around/through the site | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of scouring or other erosion within the project areas | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | All stockpiles are protected with appropriate drainage and erosion controls | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Sediment traps are free from damage and of excessive sediment deposition | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Sediment-laden stormwater is not flowing around the sediment fences or other sediment traps | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | All reasonable and practicable measures are being taken to control sediment runoff from the site | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Non-active work areas and other stabilised surfaces have a minimum 70% soil coverage | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | The site is adequately prepared for imminent and forecasted storms | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | All ESC measures are in proper working order | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | The water within sediment basins/excavations has been appropriately tested, and treated as required, to meet the required water quality prior to discharge as per the EMP | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of ponded or stagnant water | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | When working with in a waterway, all regulatory codes are in place and adhered to | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Topsoil and subsoil stockpiles are clearly signed and delineated from each other | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | All stockpiles located away from trees and drip lines | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Cultural Heritage requirements implemented as per Client direction and/or ENV P02 | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Any unexpected CH finds have been managed in accordance with the CEMP and/or ENV P02, including stopping of works in the area | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Storage of fuel/chemicals in accordance with AS1940, bunded appropriately and at distances per EMP away from drainage lines or a water course | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Safety Data Sheets (SDS) readily available for all chemicals | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | All chemicals clearly labelled | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Refuelling areas are bunded and spill kits are available | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Spill trays are being used when refuelling and not being conducted near waterways or drainage lines | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Bunds at full capacity free from rain water or spill | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Evidence of spills/ cleanup? All spills have been reported as an Environmental Incident | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Spill kits are fully stocked, including instructions/procedures for use. | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Spill kits are fully stocked, including instructions/procedures for use. | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Spill kit locations are sign-posted | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Waste oil stored/ disposed of appropriately - No leaks, spills, stains. | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Batteries stored and disposed of appropriately | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Contaminated soil/ waste segregated | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Waste is segregated appropriately for recycling | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Site free of litter/general waste/ cigarette butts | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Traffic control devices / signage correctly installed | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Regulated waste is disposed of and stored correctly | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Concrete waste is stored in a signed, lined and bunded pit | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | ENV05 Waste Materials Tracking Register up to date, and service provider dockets for Waste disposal available | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of native fauna within the projects area (No deaths, injuries or encounters) | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Significant/restricted vegetation flagged and protected | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Existing “Retained” flora is healthy and undisturbed | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Site vehicles using designated site access roads/tracks only | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of pest animals within the projects area | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of declared weeds within the projects area, access roads or right of ways | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Are vehicle weed hygiene inspection reports current and on file? | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Are stockpiled materials free from weed/pest infestation? | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | No exposed areas requiring rehabilitation | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | No mulching required (use mulch from clearing activities) | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | All soil surfaces are being appropriately prepared (i.e. pH, nutrients, roughness and density) prior to revegetation | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Rehabilitation specifics carried out as per EMP | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Stockpiles removed or stabilised and seeded as per EMP | DarrenTest | DarrenTest | 1/31/2014 12:03:00 AM |  | Yes | sunny, windy
TMR - Warrego Hwy (Toowoomba to Dalby) | Visible dust emissions controlled | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | All loads entering or leaving the site are covered and are not generating nuisance dust | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Hours of operation are complied with | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Property condition / dilapidation surveys have been conducted as required | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Appropriate drainage and ESC controls have been installed prior to work areas being cleared or disturbed | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Clean' water is being appropriately diverted around/through the site | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of scouring or other erosion within the project areas | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | All stockpiles are protected with appropriate drainage and erosion controls | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Sediment traps are free from damage and of excessive sediment deposition | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Sediment-laden stormwater is not flowing around the sediment fences or other sediment traps | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | All reasonable and practicable measures are being taken to control sediment runoff from the site | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Non-active work areas and other stabilised surfaces have a minimum 70% soil coverage | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | The site is adequately prepared for imminent and forecasted storms | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | All ESC measures are in proper working order | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | The water within sediment basins/excavations has been appropriately tested, and treated as required, to meet the required water quality prior to discharge as per the EMP | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of ponded or stagnant water | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | When working with in a waterway, all regulatory codes are in place and adhered to | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Topsoil and subsoil stockpiles are clearly signed and delineated from each other | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | All stockpiles located away from trees and drip lines | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Cultural Heritage requirements implemented as per Client direction and/or ENV P02 | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Any unexpected CH finds have been managed in accordance with the CEMP and/or ENV P02, including stopping of works in the area | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Storage of fuel/chemicals in accordance with AS1940, bunded appropriately and at distances per EMP away from drainage lines or a water course | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Safety Data Sheets (SDS) readily available for all chemicals | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | All chemicals clearly labelled | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Refuelling areas are bunded and spill kits are available | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Spill trays are being used when refuelling and not being conducted near waterways or drainage lines | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Bunds at full capacity free from rain water or spill | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Evidence of spills/ cleanup? All spills have been reported as an Environmental Incident | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Spill kits are fully stocked, including instructions/procedures for use. | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Spill kits are fully stocked, including instructions/procedures for use. | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Spill kit locations are sign-posted | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Waste oil stored/ disposed of appropriately - No leaks, spills, stains. | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Batteries stored and disposed of appropriately | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Contaminated soil/ waste segregated | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Waste is segregated appropriately for recycling | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Site free of litter/general waste/ cigarette butts | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Traffic control devices / signage correctly installed | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Regulated waste is disposed of and stored correctly | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Concrete waste is stored in a signed, lined and bunded pit | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | ENV05 Waste Materials Tracking Register up to date, and service provider dockets for Waste disposal available | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of native fauna within the projects area (No deaths, injuries or encounters) | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Significant/restricted vegetation flagged and protected | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Existing “Retained” flora is healthy and undisturbed | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Site vehicles using designated site access roads/tracks only | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of pest animals within the projects area | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | No evidence of declared weeds within the projects area, access roads or right of ways | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Are vehicle weed hygiene inspection reports current and on file? | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Are stockpiled materials free from weed/pest infestation? | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | No exposed areas requiring rehabilitation | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | No mulching required (use mulch from clearing activities) | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | All soil surfaces are being appropriately prepared (i.e. pH, nutrients, roughness and density) prior to revegetation | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Rehabilitation specifics carried out as per EMP | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
TMR - Warrego Hwy (Toowoomba to Dalby) | Stockpiles removed or stabilised and seeded as per EMP | Awais | Awais | 1/26/2014 12:03:00 AM |  | NA | Pleasant
Test project | aspect | Ahsan | Ahsan | 1/23/2014 12:05:00 AM | this is a observational comment | Yes
Test project | Aspect Item | Ahsan | Ahsan | 1/23/2014 12:05:00 AM | This is another comment | Yes
Test project | aspect | Ahsan | Ahsan | 1/23/2014 12:05:00 AM | Ahsan Inspection | Yes
Test project | Aspect Item | Ahsan | Ahsan | 1/23/2014 12:05:00 AM | Ahsan Inspection | Yes
Test project | aspect | Ahsan | Ahsan | 1/23/2014 12:05:00 AM | aa | Yes
Test project | Aspect Item | Ahsan | Ahsan | 1/23/2014 12:05:00 AM | aa | Yes
Test project | aspect | Ahsan | Ahsan | 1/23/2014 12:05:00 AM | dafg | Yes | ffs
Test project | Aspect Item | Ahsan | Ahsan | 1/23/2014 12:05:00 AM | gsgfgfd | Yes | ffs
Test project | aspect | ahsan | ahsan | 1/24/2014 12:05:00 AM | Observation 1 | Yes | kk
Test project | Aspect Item | ahsan | ahsan | 1/24/2014 12:05:00 AM | Observation 2 | Yes | kk
Test project | aspect | ahsan | ahsan | 1/24/2014 12:05:00 AM | 2 | Yes | 2
Test project | Aspect Item | ahsan | ahsan | 1/24/2014 12:05:00 AM | 2 | Yes | 2
Test project | aspect | ahsan | ahsan | 1/24/2014 12:05:00 AM | 3 | Yes
Test project | Aspect Item | ahsan | ahsan | 1/24/2014 12:05:00 AM | f | Yes
Test project | aspect | ahsan | ahsan | 1/24/2014 12:05:00 AM | 1 | Yes | 1
Test project | Aspect Item | ahsan | ahsan | 1/24/2014 12:05:00 AM | 1 | Yes | 1
Test project | aspect | ahsan | ahsan | 1/24/2014 12:05:00 AM | 3 | Yes
Test project | Aspect Item | ahsan | ahsan | 1/24/2014 12:05:00 AM | f | Yes